## Sprint-1
Epic 1: Solution Foundation
Task Name | Title | Description | Status
Task 1.1 | Create Solution Structure | MyMoneyMate.Api MyMoneyMate.Application MyMoneyMate.Domain MyMoneyMate.Infrastructure MyMoneyMate.Web MyMoneyMate.Tests
Task 1.2 | Configure Dependency Injection | ImportService IImporter ITransactionStageRepository
Epic 2: Database Setup
Task 2.1 | Create Database | MyMoneyMate
Task 2.2 | Create TransactionStage Table | StageId BatchId TransactionDate Description Amount Category Account Status ValidationMessage CreatedOn
Task 2.3 | Create ImportBatch Table | BatchId FileName ImportedDate TotalRows SuccessRows FailedRows Status
Task 2.4 | Create ImportBatchDetail Table | DetailId BatchId RowNumber ErrorMessage Status
Epic 3: Domain Layer
Task 3.1 | Create Entities | TransactionStage.cs ImportBatch.cs ImportBatchDetail.cs
Task 3.2 | Create Enums | ImportStatus Pending Valid Invalid Imported
Epic 4:Application Layer
Task 4.1 | Create DTOs | Create DTOs TransactionDate Description Amount Category Account
Task 4.2 | Create Repository Interfaces | ITransactionStageRepository IImportBatchRepository
Task 4.3 | Create Import Service | Create Import Service Read Excel Create Batch Validate Data Save Stage Records Return Batch Id
Epic 5: Infrastructure Layer
Task 5.1 | Install EPPlus
Task 5.2 | Create Excel Importer | IImporter ExcelImporter Read Excel Convert Rows Return DTO Collection
Task 5.3 - | Create Database Connection Factory | DbConnectionFactory
Task 5.4 | Create TransactionStageRepository | Insert Stage Records Retrieve Stage Records
Task 5.5 | Create ImportBatchRepository | Insert Batch Update Batch Status Get Batch Details
Epic 6: Validation
Task 6.1 - | Create Import Validator | Date Required Amount > 0 Description Required Account Required Category Required
Task 6.2 | Error Handling | Status = Invalid Store ValidationMessage Amount cannot be zero Transaction date is missing
Epic 7: API Layer
Task 7.1 - | Create ImportController | POST /api/import/upload
Task 7.2 | Create Preview Endpoint | GET /api/import/{batchId}/preview { "batchId": "xxx", "totalRows": 250, "validRows": 240, "invalidRows": 10 }
Task 7.3 | Create Batch Details Endpoint | GET /api/import/{batchId}
Epic 8: Web UI
Task 8.1 - | Upload Page | Transaction Import Choose File Upload Button
Task 8.2 | Import Summary Page | Batch Id Total Rows Valid Rows Invalid Rows
Task 8.3 | Import Detail Page | Transaction Date Description Amount Status Validation Message
Epic 9: Logging
Task 9.1 | Configure Logging | Ilogger Example Import Started Import Completed Import Failed
Task 9.2 | Exception Handling | ExceptionMiddleware Excel Errors Database Errors Validation Errors
Epic 10: Testing
Task 10.1 | Import Service Tests | Valid Excel Invalid Excel Empty Excel
Task 10.2 | Repository Tests | Insert Stage Record Create Batch Get Batch